## Launch Tracker
Item | Owner | Status | Evidence Link/Ref | ETA | Notes
Security review completion |  | In Progress |  |  | Use security-verification-checklist.md results
FERPA review |  | Pending |  |  | Technical alignment documented; legal sign-off pending
COPPA review |  | Pending |  |  | Technical alignment documented; legal sign-off pending
ClassLink/Roster 1 implementation status |  | Pending |  |  | Adapter exists; production sync completion pending
AWS hosting confirmation |  | In Progress |  |  | Confirm infra owner sign-off + env config
AWS messaging confirmation (SNS) |  | In Progress |  |  | Waiting on DevOps SNS setup/validation
User role testing |  | Pending |  |  | Test role matrix and access restrictions
Request Pullout notification testing |  | In Progress |  |  | Email path test now; SMS test after SNS ready
School onboarding procedures |  | In Progress |  |  | Validate onboarding checklist + PDF export
Documentation delivery |  | In Progress |  |  | Final docs package and links
Support plan |  | Pending |  |  | Confirm response SLA and escalation path
Backup and recovery plan |  | Pending |  |  | Add backup policy + restore drill evidence
Known limitations |  | In Progress |  |  | Keep concise list for client transparency
Final walkthrough meeting |  | Pending |  |  | Schedule after all critical items are green